INTERNAL ACTION PLAN Dr. John M. Abrahams, M.D. ¦ Three-Company Marketing Engagement

Start Date: February 16, 2026 ¦ Retainer: $7,500/month ¦ First Team Call: Monday, February 23, 2026 @ 9:00 AM

01  Company Overview  Three companies, one engagement

| Company | Focus Area | Time Allocation | Priority |
| --- | --- | --- | --- |
| Cognica Health | TMS Therapy, Spravato/Ketamine, Concussion Care, Mental Health Services (PMHNPs, LSWs) | 50% | HIGH |
| Kronos Health | Revenue Cycle Management, Out-of-Network Billing (IDR), Concussion Software, Mental Health Mgmt Software | 25% | MEDIUM |
| Institute for Spine Surgery (ISS) | Surgical practice, referral development, Google Ads repair, credentials/appointments (e.g. NY Presbyterian Hudson Valley) | 25% | MEDIUM |

02  Key Contacts & Team

| Name | Role | Responsibility | Notes |
| --- | --- | --- | --- |
| Dr. John M. Abrahams | Client / Primary Contact | Content approval (initial), strategy direction | Signs off all content |
| Juliet | Director of Operations | Schedules weekly calls, secondary approver (phased in) | Set up Monday 9 AM call |
| Sue Mogan, PMHNP | Clinical Provider | Subject matter expert for Cognica content | Aquebogue + 244 WA offices |
| Jonathan Braden (JB) | Outgoing Developer | Credentials handoff, website access, account transition | Already notified by JMA |
| Chelsea | Team Member | Aware of gettappy.com hosting mystery; may assist with transition | Coordinate on hosting |
| George Stoff (Rocket Creative) | Marketing & Brand Manager | All deliverables under SOW | rocketcreative.net |

03  Office Locations

| Location | Address | Notes |
| --- | --- | --- |
| Main Office (West Harrison) | 244 Westchester Ave, Suite 209, West Harrison NY 10604 | JMA primary + Sue Mogan sees patients here |
| Main Office (Cortlandt Manor) | 1985 Crompond Road, Suite B2, Cortlandt Manor NY 10567 | JMA primary office |
| Aquebogue Office | 508 Main Road, Aquebogue NY 11931 | Sue Mogan primary; Neurostar TMS machine here; Spravato/Ketamine coming soon |

04  Asset Inventory & Access Status

Items in red require immediate action before any content work can begin.

| Asset | Platform / Host | Status | Action Required |
| --- | --- | --- | --- |
| iss.health | GoDaddy (host + domain) | Admin access granted via email | Confirm login, audit content |
| cognifica.health | GoDaddy | 2FA on JMA's phone; JB email broken | Coordinate with JMA for 2FA bypass / account ownership transfer |
| kronoshealth.co | GoDaddy | Same config as cognifica.health | Same 2FA resolution needed |
| gettappy.com | Possibly Josh Winter's server | Unclear hosting; GoDaddy backend may help | Investigate with Chelsea; clarify ownership and DNS |
| IG: @instituteforspinesurgery | Instagram | Credentials provided | Verify login, audit posts, plan content |
| IG: @cognifica.health | Instagram | Credentials provided | Verify login, audit posts, plan content |
| Gmail (runs both IG accounts) | Google (instituteforspinesurgery@gmail.com) | Credentials provided | Secure account, enable 2FA on our end |
| LinkedIn (3 company pages) | LinkedIn | Admin access needed from JMA | Request admin access on all 3 pages (links provided) |
| Google Ads (all companies) | Google Ads | Error present; needs access | Gain account access, diagnose and fix error, rebuild structure |
| Google Business Profiles (3) | Google | Not yet created | Create or claim for ISS, Cognica, Kronos immediately |

05  Immediate Actions — Week 1 Checklist

Complete all RED items today, URGENT items by Wednesday February 18.

| Task | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Send signed SOW to JMA (confirm $7,500/month retainer, start 2/16) | George | Today 2/16 | DO TODAY |
| Invoice JMA for first month (February 16 start, pro-rate or full) | George | Today 2/16 | DO TODAY |
| Confirm Monday 9 AM weekly call is set up by Juliet; send calendar invite to full team | George + Juliet | By 2/18 | URGENT |
| Log in and verify ISS Instagram (@instituteforspinesurgery) with provided credentials | George | Today 2/16 | DO TODAY |
| Log in and verify Cognica Instagram (@cognifica.health) with provided credentials | George | Today 2/16 | DO TODAY |
| Contact JMA to resolve GoDaddy 2FA for cognifica.health and kronoshealth.co (2FA tied to JMA's phone) | George + JMA | By 2/18 | URGENT |
| Request LinkedIn admin access on all 3 company pages from JMA | George | By 2/18 | URGENT |
| Gain access to Google Ads account(s); identify and document the active error | George | By 2/18 | URGENT |
| Investigate gettappy.com hosting with Chelsea; determine if on Josh Winter's server; clarify ownership | George + Chelsea | By 2/20 | THIS WEEK |
| Create / claim Google Business Profile for Cognica Health (all 3 offices) | George | By 2/20 | THIS WEEK |
| Create / claim Google Business Profile for ISS | George | By 2/20 | THIS WEEK |
| Create / claim Google Business Profile for Kronos Health | George | By 2/20 | THIS WEEK |
| Audit existing websites (iss.health, cognifica.health, kronoshealth.co) for content, SEO baseline, broken links | George | By 2/20 | THIS WEEK |
| Audit existing social media accounts (ISS + Cognica Instagram, all 3 LinkedIn pages) for current state | George | By 2/20 | THIS WEEK |

06  30-Day Launch Roadmap

| Week | Key Actions | Milestone |
| --- | --- | --- |
| Week 1 2/16 - 2/22 | SOW signed + invoice sent. All account access resolved. GBPs created. Ads error diagnosed. Full audit complete. LinkedIn admin granted. | Accounts secured, audit complete, weekly call scheduled |
| Week 2 2/23 - 3/1 | First Monday team call (9 AM, 2/23). Present 90-day content strategy for all 3 companies. Begin building 3-month content calendar. Fix Google Ads error, rebuild campaign structure. | First call held, content strategy presented, Ads error fixed |
| Week 3 3/2 - 3/8 | Submit 3 months of content drafts to JMA for approval (social + newsletter). Update LinkedIn pages with optimized bios, services, and imagery. Launch first social posts for Cognica. | First Cognica posts live, content calendar under review |
| Week 4 3/9 - 3/15 | Content approved and scheduled for all 3 companies. First Google Ads campaigns live. March newsletters drafted. First monthly report prepared. | All channels active, first report ready for 3/16 call |

07  Recurring Deliverables (Ongoing Per SOW)

| Deliverable | Frequency | Applies To | Notes |
| --- | --- | --- | --- |
| Social Media Posts | 2-3x per week per co. | All 3 | 6-9 total posts/week minimum. Graphics, copy, hashtag strategy. |
| Google Ads Management | Ongoing | All 3 | Ad spend billed directly by Google. We manage, optimize, A/B test. |
| Monthly Newsletter | 1x per month per co. | All 3 | Content, design, distribution, list management, open/click reporting. |
| Weekly Status Update | Weekly (Mondays) | All 3 | Posts made, stats, engagement responses, upcoming items. |
| Website Updates | Quarterly | All 3 | Content refresh, new pages as needed, SEO, analytics review. |
| Monthly Performance Report | Monthly | All 3 | Analytics, recommendations, performance vs prior month. |
| Quarterly Strategy Review | Quarterly | All 3 | Planning sessions with full team; identify what is working and adjust. |

08  Cognica Health — Priority Focus (50% of Time)

Cognica is the most financially urgent company. JMA is personally absorbing its burn rate. Marketing must generate new patient inquiries for TMS, Concussion, and mental health services as quickly as possible.

| Service Line | Marketing Angle / Key Messages |
| --- | --- |
| TMS Therapy | FDA-cleared for depression; non-invasive, drug-free option; Neurostar machines at Aquebogue + West Harrison. Target: patients who have failed medication. |
| Spravato (Ketamine) | Coming soon at Aquebogue. Target treatment-resistant depression. Build anticipation now. HIPAA-compliant patient journey messaging. |
| Concussion Care | Structured concussion program. Direct provider marketing to schools, sports medicine, ERs, and primary care physicians in Westchester and Long Island. |
| Mental Health Services | Multi-tiered providers: PMHNPs (Sue Mogan) + part-time licensed social workers. Emphasize accessibility, insurance coverage, telehealth options if applicable. |

09  Account Credentials on File

The following credentials were provided by Jonathan Braden on February 16, 2026. Store securely in password manager immediately and rotate after full access transfer.

| Account | Username | Notes |
| --- | --- | --- |
| IG: @instituteforspinesurgery | instituteforspinesurgery | Gmail login: instituteforspinesurgery@gmail.com |
| IG: @cognifica.health | cognifica.health | Same Gmail account as above |
| GoDaddy (iss.health) | Admin access via email invite | Confirm credentials on first login |
| GoDaddy (cognifica + kronos) | Requires 2FA via JMA's phone | Must resolve with JMA before access |

CONFIDENTIAL — Internal use only. Rocket Creative LLC. Do not distribute.